## Defines
Modules | Team Member | Activity
MASTER | Aakash | CODING
SENSOR | Halak | DESIGN
GPS/Compass/Bridge | Vidushi | DOCUMENTATION
BRIDGE | Jay | CODE COMMENTING
BLUETOOTH | Akshata | UNIT TESTING
MOTOR | Prashant | REQUIREMENT UNDERSTANDING
HARDWARE | Saumil | REQUIREMENT ANALYSIS
| Vatsal | VERIFICATION AND VALIDATION
UI DEVELOPMENT
SUPPORT
OTHER

## Tracking Sheet
Date | Week | Activity | Team Member | Description | Hours | Module
2019-03-29 | 5 | UI DEVELOPMENT | Aakash | 1. Started designing GUI | 2 | MASTER
2019-03-29 | 5 | CODING | Aakash | 1. Interfacing Ultrasound HC-SR04 sensor with Sjone board. 2. Interfacing MaxBotix sensor with Sjone board. | 6 | SENSOR
2019-03-29 |  | Documentation | Vidushi | 1. Updated wiki schedule and BOM 2. Updated High Level Software Architecture and Team Member details on Wiki. | 6 | WIKI Report
2019-03-30 |  | Interfacing, Coding & Testing | Vidushi | 1. Interfacing of Bluetooth HC-05 Module with Sjone board and 5V power supply. 2. Worked on Data Mode(Rx/Tx) of HC-05. 3. Tested interfacing and working(Rx/TX) with Serial Monitor. | 6 | BRIDGE
2019-03-31 |  | Interfacing, Coding & Testing | Vidushi | 1. Interfacing of Bluetooth HC-05 Module withUBS TTL Convertor to configure Module. 2. Worked on Command Mode of HC-05 and configured with name Tech_Savy and changed config setting to 38400. 3. Refactoring of code for Bridge communication 4. Implemented C wrapper for UART2.cpp, uart_dev.cpp and for switch and LED files. 5. Testing done with Sample HC-05 BLE Android Application. | Almost Full Day | BRIDGE
2019-03-31 |  | Android App Development | Saumil | 1. Designed a simple app to discovery bluetooth devices nearby 2. Added buttons to turn ON and OFF bluetooth on the android phone. 3. Displayed the discovered bluetooth devices in a list view | 8 | Bridge