## Defines
Modules | Team Member | Activity
MASTER | Aakash | CODING
SENSOR | Halak | DESIGN
GPS/Compass/Bridge | Vidushi | DOCUMENTATION
BRIDGE | Jay | CODE COMMENTING
BLUETOOTH | Akshata | UNIT TESTING
MOTOR | Prashant | REQUIREMENT UNDERSTANDING
HARDWARE | Saumil | REQUIREMENT ANALYSIS
| Vatsal | VERIFICATION AND VALIDATION
UI DEVELOPMENT
SUPPORT
OTHER

## Tracking Sheet
Date | Week | Activity | Team Member | Description | Hours | Module
2019-03-29 | 5 | UI DEVELOPMENT | Aakash | 1. Started designing GUI | 2 | MASTER
2019-03-29 | 5 | CODING | Aakash | 1. Interfacing Ultrasound HC-SR04 sensor with Sjone board. 2. Interfacing MaxBotix sensor with Sjone board. | 6 | SENSOR
2019-03-29 | 5 | Documentation | Vidushi | 1. Updated wiki schedule and BOM 2. Updated High Level Software Architecture and Team Member details on Wiki. | 6 | WIKI Report
2019-03-30 | 5 | Interfacing, Coding & Testing | Vidushi | 1. Interfacing of Bluetooth HC-05 Module with Sjone board and 5V power supply. 2. Worked on Data Mode(Rx/Tx) of HC-05. 3. Tested interfacing and working(Rx/TX) with Serial Monitor. | 6 | BRIDGE
2019-03-31 | 5 | Interfacing, Coding & Testing | Vidushi | 1. Interfacing of Bluetooth HC-05 Module withUBS TTL Convertor to configure Module. 2. Worked on Command Mode of HC-05 and configured with name Tech_Savy and changed config setting to 38400. 3. Refactoring of code for Bridge communication 4. Implemented C wrapper for UART2.cpp, uart_dev.cpp and for switch and LED files. 5. Testing done with Sample HC-05 BLE Android Application. | Almost Full Day | BRIDGE
2019-03-31 | 5 | Android App Development | Saumil | 1. Designed a simple app to discovery bluetooth devices nearby 2. Added buttons to turn ON and OFF bluetooth on the android phone. 3. Displayed the discovered bluetooth devices in a list view | 8 | BRIDGE
2019-04-01 | 5 | Documentation & Interfacing | Vidushi | 1. Pushed Bridge code to gitlab 2. Hardware Interfaced compass with Sjone Board (5v) | 2 | BRIDGE & GEO
2019-04-02 | 5 | Data Sheet Reviewing | Vidushi | 1. Go through CMPS 11 datasheet in i2c & Serial Mode and read about it register settings and configurations | 2 | CMPS 11 - GEO
2019-04-03 | 5 | Documentation | Vidushi | 1. Updated wiki report with Project Title details and Car Top & side views. 2. Added Abstract and How self driving car works on Wiki. 3. Added Introduction & onjectives of Tech Savy on Wiki with High Level System Design. | 3 | WIKI Report
2019-04-04 | 5 | Documentation | Vidushi | 1. Updated wiki report with Team Members & Technical Responsibilities. 2. Updated wiki report with Team Members & Administrative Responsibilities. 3. Updated wiki report with Team Deliverables Schedule. 4. Added BILL OF MATERIALS (GENERAL PARTS) and Details on the Wiki. 5. Changed the Wiki Font , format and design for our team and added color codes for all modules. | 4 | WIKI Report
2019-04-05 | 5 | Interfacing, Coding & Testing | Vidushi | 1. Interfacing of CMPS11 with SJONE board on 3.3V. 2. Interfaced & Implement I2C Mode with CMP11 on SJOne. 3. Worked on all axis Calibration of CMPS11 using registers 0xF0, 0xF5 and 0xF6. 4. Implemented start & stop caliberation mode for CMPS 11 using command registers on SWITCH. 5. Implemented factory caliberation mode for CMPS11 on Switch in order to revert caliberation. | 4 | GEO - CMPS11
2019-04-06 | 5 | Interfacing, Coding & Testing | Vidushi | 1. Study & Implemented I2C Read/Write functions for CMPS11. 2. Implemented Heading Angle Calculation Functionality for CMPS11. 3. Refactoring of code for Geo Controller. 4. Implemented C wrapper for I2C2.cpp. | 4 | GEO - CMPS11
2019-04-08 | 5 | Documentation | Vidushi | 1. Updated wiki report with Team Deliverables Schedule Till Final Demo 2. Updated HW Block Diagrams for Bluetooth and Geo Controller | 2 | WIKI Report